## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H16E083 |  | Project Name: |  | American Furniture Demo
NPDES Id. No. | NMR10068E |  | Location: |  | 3535 Menaul Blvd NE
2025-06-17 |  | Owner |  |  |  | Contractor
Operator |  | Vista Oriente, Ltd. Co. |  |  |  | Guzman Construction Solutions, LLC
Contact name & title |  | Jeff Jesionowski |  |  |  | Eddie Gonzales
e-mail |  | jeff@amcdevelopment.net |  |  |  | eddie@guzmancs.com
Contact Phone # |  | 505-259-0991 |  |  |  | 505-975-8149
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:30am |  |  |  | Rain
Construction Phase: |  | Demolition complete | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-06-07 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP and self-inspection reports were unavailable at the time of inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a copy of your up-to-date SWPPP and self-inspection reports at the site or at an easily accessible location so that it can be made available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
2 | Stabilization - Demolition is complete and all equipment has been removed, but the disturbed soil has not been stabilized in violation of CGP Part 2.2.14. Required mitigation: Initiate the installation of stabilization measures immediately in any areas of exposed soil where construction activities have permanently ceased or will be temporarily inactive for 14 or more calendar days and complete the installation of stabilization measures as soon as practicable, but no later than 7 calendar days after stabilization has been initiated per CGP Part 2.2.14.a.ii.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | no | Latest report Date: |  | N/A
Notes:
The site is clear of demolition work. Permit coverage is still active, and the site has not been stabilized.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action