## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H17E097A |  | Project Name: |  | Burger King
NPDES Id. No. | NMR1004E4 NMR1004DZ |  | Location: |  | 2110 Carlisle Blvd. NE
2023-03-23 |  | Owner |  |  |  | Contractor
Operator |  | M&M Brothers |  |  |  | PJ Development,Inc.
Contact name & title |  | Tom McCollum |  |  |  | Pat Joseph
e-mail |  | tmgmtmmm@aol.com |  |  |  | pat@pjdev.net
Contact Phone # |  | 861-7474 |  |  |  | 263-6965
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | Excavation/grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | cloudy |  | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-03-16 |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Stabilized - After all areas have been stabilized, you must contact your Stormwater team for verification that the “Final Stabilization Criteria” of CGP 2.2.14.c has been satisfied. This step is independent of the Certificate of Occupancy (CO) process. Then satisfy the other “Conditions for Terminating CGP Coverage” per CGP 8.2 including removal of BMPs. Next, file your “Notice of Termination” (NOT) with the EPA. Please copy me with the documentation and the EPA’s acceptance of the NOT.
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | ?
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action