## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H17E097 |  | Project Name: |  | Carlisle Crossing
NPDES Id. No. | NMR1005HJ NMR10040H |  | Location: |  | 2100 Carlisle Blvd. NE
2023-03-30 |  | Owner |  |  |  | Contractor
Operator |  | Carlisle Associates LP |  |  |  | Jaynes Corp.
Contact name & title |  | Dave Rosen & Michael Falzarano |  |  |  | stetson.chandler@jaynescorp.com
e-mail |  | david@rosenmgmt & michaelf@rosenmgmt.com> |  |  |  | stetson chandler
Contact Phone # |  | 516-281-1507 |  |  |  | 432-249-0659
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 10:30pm |  |  |  | Rain
Construction Phase: |  | Parking lot done, no construction, landscaping and building incomplete. | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-03-16 |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The NMDES ID# for the Owner is wrong on the Posting. It should be NMR1005HJ
2 | Please provide latest self-inspection report and all future reports.
General information comment - Loading docks next to east side of building, two Pad sites, and all landscaping are still disturbed and need to be stabilized. - You must continue permit coverage, self-inspections, SWPPP and BMP maintenance until the City determines that the Final Stabilization Criteria CGP2.2.14.c has been satisfied. Then you must remove the BMPs and send documentation of the Final Stabilization to the EPA with a Notice of Termination (NOT) per CGP 8.2 to end your coverage under the CGP. This step is independent of the Work Order. Please copy me with the documentation and the EPA’s acceptance of the NOT at that time. In the meantime seed and Hydromulch are required per CGP 2.2.14.
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | ?
Notes:
New building construction not started. Parking lot complete. Burger King complete by others. Whole foods foundation and north wall under construction by others. No construction equipment or personel were present on this site at the time of inspection.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-803-6155)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action