## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  |  | 21st Century Academy
Location: |  |  | 4300 Cutler NE
Site Contact Name & Agency |  |  | William Cervantes |  |  |  | ESC File No. | H17E115
|  |  | William Cervantes Enterprises |  |  |  | NPDES Id. No.
Inspection Date: |  |  | 2019-05-23 | Start/End Time: |  | 9:40 |  | 10:00
CoA Stormwater Inspector: |  |  |  | Curtis Cherne | [9 empty] | Rain
Construction Phase: |  |  | bldg nearly complete, prepping to pave | [10 empty] | Clear/ Windy
Type of Inspection: |  | X | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  |  | Clear/ Windy |  |  | Temperature: ~ |  |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2019-05-10 | [5 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [13 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | track-out onto access drive and sediment in gutter.
2 | wash-out south side of bldg
3 | wash-out northwest of bldg
4 | gap in sediment BMP north side, sediment on asphalt, area drains over parking lot out to the street
5 | dirt/rocks in Cutler Ave.
Yes
2.1 | Discharge off site? (Y/N) |  |  |  | No | [7 empty] | No
4 | Self Inspection Reports |  |  |  | request |  | Latest report Date: |  | 2019-05-16
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  |  | Curtis Cherne PE, 505-924-3420
|  |  | ccherne@cabq.gov |  |  |  |  | 2019-05-23

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action