## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H18E070 |  | Project Name: |  | McDonald's 30-0001
NPDES Id. No. | NMR1005YE |  | Location: |  | 5900 Menaul Blvd NE
2023-11-08 |  | Owner |  |  |  | Contractor
Operator |  | McDonald's USA, LLC
Contact name & title |  | Alex Breeden
e-mail |  | alex.breeden@us.mcd.com
Contact Phone # |  | 630-207-0289
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: | 1pm |  |  |  | Rain
Construction Phase: |  | demo | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2023-09-14 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Permit coverage posting was missing in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5
2 | The SWPPP was unavailable during the inspection in violation of CGP Part 7.3. Required mitigation: You must keep a current copy of your SWPPP at the site or at an easily accessible location so that it can be made available at the time of an on-site inspection per CGP Part 7.3. Since there was no posting, there was no contact information to call and locate the SWPPP.
3 | There were gaps in the straw wattles around the perimeter of the construction site in violation of CGP Part 2.1.3. Required mitigation: You must complete installation of stormwater controls by the time each phase of construction activities has begun per CGP Part 2.1.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date:
Notes:
Inspection performed on first day of demo
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action