## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H18E070 |  | Project Name: |  | McDonald's 30-0001
NPDES Id. No. | NMR1005YE |  | Location: |  | 5900 Menaul Blvd NE
2023-11-22 |  | Owner |  |  |  | Contractor
Operator |  | McDonald's USA, LLC |  |  |  | Barnsley Construction
Contact name & title |  | Alex Breeden |  |  |  | Ray Casias
e-mail |  | alex.breeden@us.mcd.com |  |  |  | rayc@barnsleyconstruction.com
Contact Phone # |  | 630-207-0289 |  |  |  | 505-856-5576
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1215pm |  |  |  | Rain
Construction Phase: |  | demo | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-11-20 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP was unavailable during the inspection in violation of CGP Part 7.3. Required mitigation: You must keep a current copy of your SWPPP at the site or at an easily accessible location so that it can be made available at the time of an on-site inspection per CGP Part 7.3. Since there was no posting, there was no contact information to call and locate the SWPPP. Missing items in the electronic SWPPP sent prior to completing report. Ensure these are corrected in the on-site SWPPP: The owner needs to certify the SWPPP, Identify personnel responsible for installation and maintenance of BMPs, ensure stormwater team has required training for their responsibility, estimated phases of construction.
2 | There were gaps in the straw wattles around the perimeter of the construction site and track-out pads were not installed in violation of CGP Parts 2.1.4 and 2.2.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition druing permit coverage and are protected from activities that would reduce their effectiveness, per CGP Part 2.1.4. Minimize sediment track-out and implement track-out controls as necessary to ensure sediment removal occurs prior to vehicle exit per CGP Part 2.2.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
Previous inspection found Posting missing, SWPPP missing, gaps in perimeter wattles
SWPPP location contact was called, sent electronic version.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action