## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H18E070 |  | Project Name: |  | McDonald's 30-0001
NPDES Id. No. | NMR1005YE |  | Location: |  | 5900 Menaul Blvd NE
2023-12-14 |  | Owner |  |  |  | Contractor
Operator |  | McDonald's USA, LLC |  |  |  | Barnsley Construction
Contact name & title |  | Alex Breeden |  |  |  | Ray Casias
e-mail |  | alex.breeden@us.mcd.com |  |  |  | rayc@barnsleyconstruction.com
Contact Phone # |  | 630-207-0289 |  |  |  | 505-856-5576
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1:30pm |  |  |  | Rain
Construction Phase: | [11 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-12-14 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The self-inspection reports are missing both of the operators' signatures in violation of CGP Part 4.7.2. The modified SWPPP map showing the new construction exit location is missing certification of the operators in violation of CGP Part 7.4.3 Required mitigation: Each inspection report and SWPPP modification must be signed by the operator's signatory in accordance with CGP Appendix G, Part G.11. You must also maintain records showing the dates of all SWPPP modifications which must include the name of the person who authorized each change per CGP Part 7.4.2. Please note that the Delegation of Authority to sign inspection reports and SWPPP modifications cannot be to a third party, and must be a representative of each operator.
2 | Track-out - Sediment has been tracked-out of the site in violation of CGP Part 2.2.4. Required mitigation: Implement additional track-out controls as necessary to ensure that sediment removal occurs prior to vehicle exit, and where sediment has been tracked-out from your site onto paved roads, sidewalks, or other paved areas outside of your site, removed the deposited sediment by the end of the same business day in which the track-out occurs, as per CGP Part 2.2.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2023-12-11
Notes:
Previous inspections found Posting missing, SWPPP missing, gaps in perimeter wattles
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action