## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. |  |  | Project Name:
NPDES Id. No. |  |  | Location:
2022-04-20 |  | Owner |  |  |  | Contractor
Operator |  | Template
Contact name & title
e-mail
Contact Phone #
COA Inspector |  | Doug Hughes | [8 empty] | Rain
Construction Phase: | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint | Follow Up |  | Windy
Clear
Weather at time of inspection? | [5 empty] | Temperature: ~ |  |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [10 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | NOI - Your CGP coverage, NPDES ID# NMR100xxx, expired on 2/17/22 before the construction and stabilization were complete in violation of CGP1.4.3., or The property owners NOI wasn't approved by the City in Violation of City Ordinance § 14-5-2-11(A). Required Mitigation: The property owner’s NOI and ESC Plan must be submitted to the City of Albuquerque for review and approval per Albuquerque’s Erosion and Sediment Control (ESC) ordinance § 14-5-2-11(A).
2 | Stabilization – “large bare areas” still exist contrary to the CGP 2.2.14.c.i “Final Stabilization Criteria.” Required Mitigation: Stabilize the inactive disturbed areas and “large bare areas” per CGP 2.2.14.c.i. Implement and maintain stabilization measures in areas that remain inactive for 14 days or more. Measures must be initiated within 14 days and completed no later than 14 days per CGP 2.2.14.
3 | Posting - CGP coverage was not posted so it is visible from the public road nearest to the active part of the construction site, using a font large enough to be readily viewed from a public right-of-way in violation of CGP 1.5. Required Mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way per CGP 1.5.
4 | The SWPPP and self-inspection reports were not available on-site during the inspection in Violation of CGP 7.3, City Ordinance § 14-5-2-11(C)(1), and CGP 4.7.3. Required Mitigation: The SWPPP, including the SWPPP Map, Self Inspection Reports, and Corrective Action Reports, must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site CGP 7.3.
5 | Sediment had been discharged in stormwater or tracked out from the site and deposited in the adjacent street and not removed within 24 hours in violation of CGP 2.2.4.d. Required mitigation: Remove sediment deposited in the streets by the end of the same business day. Remove the sediment by sweeping, shoveling, or vacuuming these surfaces or using other similarly effective means of sediment removal. You are prohibited from hosing or sweeping sediment per CGP 2.2.4.d.
6 | BMPs - Erosion and sediment controls were not implemented and maintained to minimize the discharge of pollutants in stormwater from this site in violation of CGP 2.1 There were no perimeter controls on the lots to keep sediment and other pollutants out of the street in violation of CGP 2.2.3. The inlet protection was missing and the pond didn't have any retention to serve as a temporary sediment basin (SB) in violation of CGP2.2.10 and 2.2.12. Required mitigation: If at any time you find that a stormwater control needs routine Maintenance, you must immediately initiate the needed maintenance work and complete such work by the close of the next business day. When the problem requires a new or replacement control or significant repair, install the new or modified control and make it operational or complete the repair by no later than seven (7) calendar days from the time of discovery per CGP 5.2.1. Provide either curb cutbacks or a silt fence between the lots and the street per CGP 2.2.3, inlet protection per CGP 2.2.10, and a temporary sediment basin per CGP 2.2.12 The SB outlet structure must temporarily withdraw water from the surface of the sediment basin until construction and stabilization is complete.
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | requested | Latest report Date: |  | ?
Notes:
The SWPPP was not on site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action