## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H19E090 |  | Project Name: |  | US Eagle FCU Menaul Branch | [5 empty] | 505-342-8888
NPDES Id. No. | NMR1003M3/NMR1003MO |  | Location: |  | 7201 Menaul Blvd. NE
2021-06-03 |  | Owner |  |  |  | Contractor
Operator |  | US Eagle FCU |  |  |  | Enterprise Builders |  |  |  |  | Tim Slatunas
Contact name & title |  | Michael Moore |  |  |  | Ralph Baldwin
e-mail |  | mmoore@useagle.org |  |  |  | rpb@ebnm.com
Contact Phone # |  | 505-342-8888 |  |  |  | 505-857-0050
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 3:15 PM-3:25 PM |  |  |  | Rain
Construction Phase: |  | infrastructure | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 88 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-31 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Sediment on sidewalk. Reposition mulch socks to prevent sediment from exiting the site. Sweep track-out and sediment daily. | [9 empty] | 2021-05-03
2 | Wind screen missing in some sections. Install wind screen across all sections of the perimeter fence as shown in the ESC Plan. | [9 empty] | 2021-05-31
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Received | Latest report Date: |  | 2021-06-09
Notes: | Nobody from Enterprise Builders on site. Only TLC Plumbing was working on site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action