## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H20E003D |  | Project Name: |  | Raising Cane's
NPDES Id. No. | NMR1004AL |  | Location: |  | 2004 Wyoming Blvd NE
2023-04-19 |  | Owner |  |  |  | Contractor
Operator |  | Raising Cane's Restaraunts LLC |  |  |  | MAPP
Contact name & title |  | Robert Montgomery |  |  |  | Victor Jacques
e-mail |  | rmontgomery@raisingcanes.com |  |  |  | vjacques@MAPPbuild.com
Contact Phone # |  | 972-769-3357 |  |  |  | 972-839-0343
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 11:30am |  |  |  | Rain
Construction Phase: |  | Certificate of Occupancy | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 62 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-03-16 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The City has determined that the ground cover on Tract 1 satisfies the Final Stabilization Criteria CGP2.2.14.c, so you must remove the BMPs and send documentation of the Final Stabilization to the EPA with a Notice of Termination (NOT) per CGP 8.2 to end your coverage under the CGP. This step is independent of the Building Permit and Certificate of Occupancy. Please copy me with the documentation and the EPA’s acceptance of the NOT.
2
3
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | n/a
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action