## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H20E003E |  | Project Name: |  | Starbucks Albuquerque
NPDES Id. No. | NMR10055D |  | Location: |  | 2004 Wyoming
2024-08-28 |  | Owner |  |  |  | Contractor
Operator |  | WFC Wyoming NM LLC |  |  |  | Hart Design and Construction
Contact name & title |  | Renaldo Gallagher |  |  |  | Andy Hart
e-mail |  | rgallagher@westfin.com |  |  |  | ahart@construction.net
Contact Phone # |  | 770-344-8962 |  |  |  | 505-345-4001
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | verticals, utilities | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 40 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-06-10 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | None
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
SWPPP is located in the Conex Box.
The Delegation of Authority is missing a signature.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action