## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H20E003D_S |  | Project Name: |  | Demolition and stabilization
NPDES Id. No. | NMR10055D |  | Location: |  | 2004 Wyoming Blvd NE
2023-04-19 |  | Owner |  |  |  | Contractor
Operator |  | WFC Wyoming NM LLC |  |  |  | MAPP
Contact name & title |  | Renaldo Gallagher |  |  |  | Victor Jacques
e-mail |  | rgallagher@Westfin.com |  |  |  | vjacques@MAPPbuilt.com
Contact Phone # |  | 770-344-8962 |  |  |  | 972-839-0343
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 11:30am |  |  |  | Rain
Construction Phase: |  | Bare Dirt - Construction is Inactive | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 62 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-03-16 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Permit coverage wasn't posted. You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of- way per CGP 1.5
2 | SWPPP wasn’t available on site at time of inspection, so it couldn't be checked to see if it is up-to-date. - Provide a scanned copy of the up-to-date SWPPP with all reports to the Storm Water Quality Section at 600 2nd St NW suite 400 - Jhughes@cabq.gov - Per CGP 4.8.2
3 | Silt Fence and Stabilization were missing from the south half of this site where you demolished the building and parking lot. You must now apply cover per CGP 2.2.14 and install the missing silt fence. The inlets in Raising Cane’s parking lot drain to the City’s MS4 and into the Rio Grande. Keep sediment out of the storm drain.
You must continue permit coverage, self-inspections, SWPPP and BMP maintenance until the City determines that the Final Stabilization Criteria CGP2.2.14.c has been satisfied Then you must remove the BMPs and send documentation of the Final Stabilization to the EPA with a Notice of Termination (NOT) per CGP 8.2 to end your coverage under the CGP.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | n/a
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action