## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H21E020 |  | Project Name: |  | Nusenda Credit Union
NPDES Id. No. | NMR1005OR |  | Location: |  | 2801 Juan Tabo Blvd NE
2024-08-28 |  | Owner |  |  |  | Contractor
Operator |  | Nusenda Federal Credit Union |  |  |  | Enterprise Builders
Contact name & title |  | Tim Wright |  |  |  | Darren Lewis
e-mail |  | twright@nusenda.com |  |  |  | dlewis@ebnm.com
Contact Phone # |  | 505-796-2806 |  |  |  | 505-263-3951
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 3pm |  |  |  | Rain
Construction Phase: |  | verticals, utilities | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | cloudy |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-07-27 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The self-inspection reports need to be signed by both operators in violation of CGP Part 4.7.2. Required mitigation: Each inspection report must be signed by the operator's signatory in accordance with CGP Appendix G, Part G.11.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2024-08-27
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action