## Sheet1
UPPER PETROGLYPHS TIA COMMENTS
20190342
Comment # | PAGE | COMMENT | SOURCE | REVIEWER | RESPONSE | CHECKED BY | LEGEND
1 | general | There is supposed to be a 2040 horizon year analysis. Will this be provided later? | Bernalillo County
2 | general | Add recommendations on internal roads per scenario. Ex. 2024 recommendations: construct Arroyo Vista half section, Estancia Pkwy with two directional lanes/half section, Dell Webb full section for the extent provided in Figure 3. | Bernalillo County | AG | Will add more roadway recommendations to section on page 8 | CDV | GREEN | Resolved/Present In Report, may need to be elaborated to Dept who asked
3 | 7 | New MTP Update cycle with socioeceonomic analysis/travel demand update every 5 years, update language to reflect correct cycle length | Bernalillo County | AG | Done | CDV
4 | general | Tempur Pedic Parkway > Comfort Way, update names | Bernalillo County | AG | Done | CDV | YELLOW | Can Respond to Comment - will need concurrence from client for additional effort
5 | 4,8 | 2024/2027 Atrisco Vista/Comfort Way recs do not match analysis config, NBR lanes warranted according to COA | Bernalillo County | AG | The text in Build 2024 recommendations is correct. Appendix has been updated | CDV
6 | 9 | 2027 Atrisco Vista/118th recs do not match analysis config, lane recs to be verified, NBR in the PM warranted by COA | Bernalillo County | AG | Add WB dedicated right and left and NB right in text and analysis | CDV | ORANGE | Uncertain action, need to discuss with Dept for more information
7 | general | 2027 Atrisco Vista/Arroyo Vista NBR, SBL meets COA Warrant | Bernalillo County | AG | Add NB Right and SB Left in text and Analysis | CDV
8 | 9 | 2034 Arroyo Vista/Atrisco Vista specify lane configuration, analysis does not support expansion to the full section (6 lanes) | Bernalillo County | AG | Added specific lane configuration and verified half section (2 lane) operates well. | CDV | RED | Cannot be resolved without more data/information
9 | 9 | 2034 Why is Arroyo vista recommended to widen with LOS C? | Bernalillo County | AG | Done - Updated recommendation to 2 lane section to 2034 build out year. | CDV
10 | 9 | 2034 Atrisco Vista/Ladera include rec turn lane config (different northbound lane config between AM and PM) | Bernalillo County | AG | Done - Updated AM to match PM analysis | CDV
11 | 9,10 | 2034 Estancia/Ladera currently modeled 2 ways, confirm correct config | Bernalillo County | AG | TWSC fails, AWSC does not. Included both in report to prove out AWSC recommendation. | CDV
12 | general | 2034 Del Webb Prkwy recommend correction on construction sections | Bernalillo County | AG | noted in 2034 recommendations | CDV
13 | 5 | 2027 Build, first sentence of section missing language | Bernalillo County | AG | Done - Revised run on sentence | CDV
14 | 28 | Arroyo Vista to Atrisco Vista, Figure 3 to reflect connection by Ph1 | Bernalillo County | AG | Figure 3 on Page 15 will reflect note on connection | CDV
15 | 29 | 2034 Arroyo Vista 2-lane (ex) or 4-lane (rec), which one? | Bernalillo County | AG | Recommend 2-lane for all build out years | CDV
16 | 76-79 | Ladera Parkway > Ladera Drive | Bernalillo County | AG | Done | CDV
17 | 126-127 | Reflect language for 2034 Estancia/Ladera on correct lane config (rec?) | Bernalillo County | AG | Done - Noted on 126 | CDV
18 | general | review development pace, adjust infrastructure improvement to correlate build changes | City of Albuquerque | AG | Will Review development pace as construction occurs. | CDV
19 | general | construct traffic signals at recommended intersections | City of Albuquerque | AG | No addressing needed | CDV
20 | general | traffic signal warrants for ALL recommended traffic signals | City of Albuquerque | AG | No addressing needed | CDV
21 | general | confirm if comments dated july 20, 2020 were previously addressed, provide resolution matrix (specifically lane utilization @ I-40/NM 500) | NMDOT | AG | As this movement is not a triple right any longer, the lane utilization factors have changed since this comment was generated. The lane utilization has been updated based on large vehicles wanting to be in the far left lane turning right to access the industrial sites and passenger vehicles wanting to be in the inside right turning lane | CDV
22 | general | 2045 Horizon Year Analysis requested in report | NMDOT
23 | general | Signal Timing for Central/Atrisco Vista? Include in Appendix, coordinated? | NMDOT | AG | Done - Added in Appendix | CDV
24 | general | queue summary of existing turn bay lengths, proposed queue from signalized intersections, SAMM compliance? | NMDOT |  | Included in Appendix. Do you want a summary in the report?
25 | general | mitigated section at the end of each intersection analysis, refer to appendix, signal timing adjustments always included? Clarify | NMDOT |  | Add an Appendix for each Build year with Mitigations only?
26 | general | Mitigated analysis signal timing recs include a coordinated NM500? | NMDOT | AG | Yes, this is included in the report | CDV
27 | general | Warrant study for all signal warrants recommended | NMDOT |  | "For all future studies"?
28 | general | crash summary report to be added | NMDOT |  | Is crash study required?
29 | general | conceptual drawings for all recommendations | NMDOT |  | Conceptual Drawings were not a part of the initial scope.
30 | general | addition of roadway connections and assumptions of diverted traffic | NMDOT |  | Diverted traffic was included on page 28 of the TIA. 25% of the Atrisco Vista traffic will use Arroyo Vista. Clarification of other roadway connections?
31 | general | Multi period analysis when V/C<1 | NMDOT |  | Are there specific examples in this TIA where that did not occur?
32 | 1 | Expand upon "other large economic development projects" around the UP | NMDOT | AG | These may or may not be within the UP masterplan. We don't know the timeframe of these other developments currently. This statement is saying that if there are any others, they will require there own TIA. | CDV
33 | 2 | Mapping that identifies the existing and future intersections | NMDOT | AG | Figure 6 shows each intersection. Intersections with F or E are future intersections. Can update if needed. | CDV
34 | 19 | Include Roadway jurisdictions/boundaries (I-40, Atrisco Vista/NM500, 98th, Unser, Central) | NMDOT | AG | Done - Noted in report | CDV
35 | 26 | Figure 4 difficult to tell what is included in the phases | NMDOT | AG | Will update with better figure and key for each phase | CDV
36 | 27 | Figure 5 Add Key | NMDOT | AG | Will update with better figure for each phase | CDV
37 | 28 | Atrisco Vista/Arroyo Vista show connected in 2024 | NMDOT | AG | Revise additional figures to make note of connection on Figure 3, Ask Matt | CDV
38 | 50 | Recommend Signalization of the interchange ramp (?) | NMDOT | AG | Done - | CDV
39 | 50 | Expand upon "Adj" in the description | NMDOT | AG | Bills' revised formatting naming convention | CDV
40 | 51 | approach LOS for each table in NB, Build scenarios | NMDOT | AG | Will include approach LOS for all NMDOT intersections in tables | CDV
41 | 58 | intersection LOS for each unsignalized intersection summary results | NMDOT | AG | Will include overall LOS for unsignalized intersection summaries | CDV
42 | 60 | Signal warrant analysis checked for I-40 EB/NM500? | NMDOT | AG | Yes, will include in report. | CDV
43 | 62 | mitigated signal timing adjustments for I-40/AV EB Ramps? | NMDOT |  | will report mitigated signal timing. For clarification, do you want these values for dual SB Left or single SB Left?
44 | 62 | I-40 EB offramp laneage configuration completed by Amazon included in part of existing conditions analysis? | NMDOT | AG | Yes, all laneage constructed was included in analysis | CDV
45 | 66 | NMDOT study not recommending a triple right config for I-40 WB | NMDOT | AG | No Triple right was analyzed. Addressed in report. | CDV
46 | 66 | I-40 WB off-ramp/NM500 provide conceptual drawing of pre-left config | NMDOT |  | Conceptual Drawings were not a part of the initial scope.
47 | 82 | Include all lane movements which are LOS E/LOS F in summary table | NMDOT | AG | Will include approach LOS for all NMDOT intersections in tables | CDV
48 | 84 | Where is the 98th/EB Ramps analysis section? | NMDOT | AG | 98th/EB Ramps are included in the Unsignalized intersections portion of the report starting on page 119 | CDV
49 | 93 | I-40 EB/Unser signal warrant analysis in 2019 condition | NMDOT |  | Updated 12 hour traffic counts will be needed to complete full signal warrant analysis. See comment 53
50 | 99 | Table 82 included movements of LOS E/F (ALL NB/Build tables) | NMDOT | AG | Will include approach LOS for all NMDOT intersections in tables | CDV
51 | 128 | Provide overall map with the freeway segments labeled | NMDOT |  | Can include freeway segment figure
52 | 138 | List NMDOT control improvements on a timeline | NMDOT | AG | Done | CDV
53 | 139 | NMDOT to verify full signal warrant analysis for I-40 EB/Unser | NMDOT | AG | NMDOT will handle this warrant analysis?
54 | 140 | 2-stage left turns not accepted | NMDOT |  | 2-stage fails as well. Remove out 2 stage analysis?
55 | 140 | Full signal warrant analysis requested for any signal warranted in build year | NMDOT | AG | Added in general recommendations | CDV
56 | 141 | Atrisco Vista/I-40 recommended striping changes? | NMDOT | AG | Noted, restriping to result in dual WBR lanes and additional 2 lanes for pre-left | CDV
57 | 144 | Conceptual drawing of an additional EB lane on I-40 between Arroyo Vista/Unser | NMDOT |  | Conceptual Drawings were not a part of the initial scope.
58 | 144 | I-40 WB/NM500 verify triple WBR (instead of dual WBR lane rec by NMDOT) | NMDOT | AG | No Triple right was analyzed. Addressed in report. | CDV
59 | 144 | I-40 EB/NM500, update signal timing with second SBL? Protected? Can it be served twice with proposed signal coordination? | NMDOT |  | Pre-lefts MUST remain for the WB intersection to operate without LOS F movement southbound. The Pre Left was also included in the NMDOT study that was conducted. The southbound left will be protected. More information from the NMDOT will be needed to resolve this comment