## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | J08E003B |  | Project Name: |  | Savio Ridge Units 1 & 2
NPDES Id. No. | NMR100789 |  | Location: |  | Arroyo Vista Blvd
2025-10-29 |  | Owner |  |  |  | Contractor
Operator |  | Pulte Homes
Contact name & title |  | Kevin Patton
e-mail |  | kevin.patton@pultegroup.com
Contact Phone # |  | 238-2857
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 1pm |  |  |  | Rain
Construction Phase: |  | Rough Grading U1 & 2 complete Storm Drain started in NW cor | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 65 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-10-14 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | None
2
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | OK | Latest report Date: |  | 2025-10-30
Notes: | SWPPP is in lock box on back of Posting 100 yd west of main entrance
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action