## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File # | J08E003B |  | Project Name: |  | Savio Ridge Units 1 & 2
NPDES ID # | NMR100789 |  | Location: |  | 1600 Arroyo Vista Blvd NW
2026-02-19 |  | Owner |  |  |  | Contractor
Operator |  | Pulte Homes
Contact name & title |  | Keven Patton and Cody Walton
Contact e-mail |  | kevin.patton@pultegroup.com | [9 empty] | Snow
Contact Phone # |  | 505-238-2857 | [9 empty] | Clear
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:30am |  |  |  | Rain
Construction Phase: |  | Grading, curb and gutter | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 40° |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2026-01-08 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | None
Yes
| Discharge off-site? |  |  | No | [6 empty] | No
| Self-Inspection Reports? |  |  | Yes | Latest report Date: |  | 2026-02-05
Notes: | The SWPPP is in a lockbox on the back of Posting 100 yd west of the main entrance.
Cody Walton needs to sign the recent self-inspection reports in the SWPPP book.
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action