## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | J08E005 |  | Project Name: |  | Inspiration Subdivision
NPDES Id. No. | NMR1004Y9 |  | Location: |  | Arroyo Vista Blvd and High Mesa Dr
2023-07-21 |  | Owner |  |  |  | Contractor
Operator |  | Pulte Homes |  |  |  | Pulte Homes
Contact name & title |  | Kevin Patton |  |  |  | Matt Sena
e-mail |  | kevin.patton@pultegroup.com |  |  |  | Matt.Sena@Pulte.com
Contact Phone # |  | 505-341-8591 |  |  |  | 505-603-7159
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1030am |  |  |  | Rain
Construction Phase: |  | Construction | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-05-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | None
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2023-07-13
Notes: | The SWPPP is in the construction trailer in NE corner of site on Kachina Peak Tr.
There is a clear Delegation of Authority to Matt Sena.
Severe erosion around rip rap rundowns in dirt pond on Angel Fire Trail. Repair and stabilization are needed. HOA Tracts need stabilization after 14 days of construction inactivity. One instance of washout was noted, but vastly improved from previous inspections.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action