## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  | Fed Ex Brunacini Warehouse
Location: |  | 7601 Los Volcanes Rd
Site Contact Name & Agency |  | John Trujillo - Brunacini |  |  |  | ESC File No. | J10E002G
|  | jtrujillo@brunacini.com |  |  |  | NPDES Id. No. | NMR100YX
Inspection Date: |  | 2019-07-08 | Start/End Time: |  | 1400/1500hrs
CoA Stormwater Inspector: |  |  | Timothy E. Sims | [9 empty] | Rain
Construction Phase: |  | site work and vertical | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint | x | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  |  | Temperature: ~ |  |  | 89* |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [8 empty] | 2019-07-07 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Washout is on the NE area of site. Please clean and remove washout. Have trades use washout
facility
2 | Construction and domestic waste not in acceptable waste container. Please mitigate and have
workers utilize provided waste containers.
3 | Please provide a sediment BMP on the west entrances (Gallatin)
4 | The stock pile on the SW corner of site will require a sediment BMP on the downhill side.
Please provide a sediment BMP.
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [7 empty] | No
4 | Self Inspection Reports |  |  | requested |  | Latest report Date: |  | 06.13.19
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Timothy E. Sims - (505) 803-6155
|  | tsims@cabq.gov |  |  |  |  | 2019-07-08

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action