## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  | Ben E. Keith
Location: |  | 601 Gallatin Pl. NW
Site Contact Name & Agency |  | Thomas Hays - ESI Constructors |  |  |  | ESC File No. | NMR10023X
|  | thays@esigroupusa.com |  |  |  | NPDES Id. No. | J10E002G1
Inspection Date: |  | 2019-09-20 | Start/End Time: |  | 0830/0850hrs
CoA Stormwater Inspector: |  |  | Timothy E. Sims | [8 empty] | Rain
Construction Phase: |  | earthwork | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  | 311/Complaint | x | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  |  | Temperature: ~ |  | 66* |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2019-09-11 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
All previous issues mitigated, no new issues observed with this inspection.
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  |  |  | Latest report Date:
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Timothy E. Sims - (505) 803-6155
|  | tsims@cabq.gov |  |  |  |  | 2019-09-20

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action