## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | J10E027 |  | Project Name: |  | Rays Flooring Phase 1 Tenant Addition
NPDES Id. No. | NMR10060R |  | Location: |  | 7401 Los Volcanes Rd NW
2024-08-08 |  | Owner |  |  |  | Contractor
Operator |  | GDCLV, LLC |  |  |  | Enterprise Builders
Contact name & title |  | Ventura Ruybal |  |  |  | Chris Baca
e-mail |  | vruybal@raysflooring.com |  |  |  | cbaca@ebnm.com
Contact Phone # |  | 505-883-1967 |  |  |  | 505-857-0050
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 97 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-07-27 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The stormwater team needs to be identified in the SWPPP in violation of CGP Part 7.2.2. The SWPPP has not been certified by any operators in violation of CGP Part 7.2.10. The operators' NOIs were not included in the on-site SWPPP in violation of CGP Part 7.2.11. Required mitigation: Identify the personnel (by name and position) that you have made part of the stormwater team, as well as their individual responsibilities, including which members are responsible for conducting inspections. The responsibilities include personnel responsible for 1) design, 2) installation, 3) maintenance and/or 4) repair of stormwater controls, along with those responsible for treatment chemicals, 5) conducting inspections, and 6) those responsible for taking corrective actions per CGP 6.1 and 7.2.2. Your signatory must sign and date your SWPPP in accordance with CGP Appendix G, Part G.11 per CGP Part 7.2.10. You must include a copy of your NOI submitted to the EPA along with any correspondence exchanged between you and EPA related to coverage under this permit per CGP Part 7.2.11.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | QR Code | Latest report Date: |  | 2024-08-08
Notes:
SWPPP was in doc-box located near the permit coverage posting.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action