## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | J10E027 |  | Project Name: |  | Rays Flooring Phase 1 Tenant Addition
NPDES Id. No. | NMR10060R |  | Location: |  | 7401 Los Volcanes Rd NW
2025-06-03 |  | Owner |  |  |  | Contractor
Operator |  | GDCLV, LLC |  |  |  | Enterprise Builders
Contact name & title |  | Ventura Ruybal |  |  |  | Chris Baca
e-mail |  | vruybal@raysflooring.com |  |  |  | cbaca@ebnm.com
Contact Phone # |  | 505-883-1967 |  |  |  | 505-857-0050
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 10:15am |  |  |  | Rain
Construction Phase: |  | interior | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-06-02 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The SWPPP needs to be certified by the owner (GDCLV, LLC) in violation of CGP Part 7.2.10. The inspection reports were not available for the inspection in violation of CGP Part 4.7.3. Required mitigation: Your signatory must sign and date your SWPPP in accordance with Appendix G, Part G.11. You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP part 4.7.3.
2 | One of the porta potties had been tipped over and was lying on its side in violation of CGP Part 2.3.3.f. Required mitigation: Position portable toilets so they are securre and will not be tipped over per CGP Part 2.3.3.f.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | QR Code | Latest report Date: |  | 2025-05-29
Notes:
SWPPP is in construction office
Inspection reports must be available on-site "same as paper"
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action