## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | J10E048 |  | Project Name: |  | FedEx Stockpile - Tract D | [6 empty] | Brad Frosch (bfrosch@tierrawestllc.com)
NPDES Id. No. | NMR1002UH |  | Location: |  | Fortuna Rd. NW | [8 empty] | Zeke Mares <Zeke.Mares@feinm.com>
2022-02-28 |  | Owner |  |  |  | Contractor | [5 empty] | abrunacini@brunacini.com
Operator |  | Yankee Fans, LLC. |  |  |  | Franklins | [7 empty] | Jesus Jurado <Jesus.Jurado@feinm.com>
Contact name & title |  | Angleo Brunacini |  |  |  | John Ellis | [5 empty] | gary.huffman@feinm.com
e-mail |  | abrunacini@brunacini.com |  |  |  | John.Ellis@feinm.com | [7 empty] | VCarrica@tierrawestllc.com
Contact Phone # |  | 505-991-2233 |  |  |  | 505-975-2878 | [5 empty] | John Ellis <John.Ellis@feinm.com>
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 3pm |  |  |  |  | Rain |  | Gus.Harbaugh@feinm.com
Construction Phase: |  | Stabilization | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy |  | vperea@tierrawestllc.com
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 60 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-01-01 |  |  |  |  | 2021-02-22 |  | Sleet |  | Brad.Graham@feinm.com
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [13 empty] | gary.huffman@feinm.com
1 | Silt fence missing along north side. Excess sediment acumulation south side. Repair/maintain silt fences.
2 | Site is not stabilized. Implement stabilization controls per CGP 2.2.14. Offsite area south of site disturbed by this project is full of tumble weeds that exceed the 4" max height and width but no perinial vegitation (final stabelization criteria not met and weed ordinance violation in disturbed offsite area)
3 | Provide latest self inspection report
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2022-02-24
Notes: | site is inactive and partially transferred to APS, ponding on east side of site transferred
to APS so this site has increased uncontroled runoff.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action