## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | J10E049 |  | Project Name: |  | Coors/Bluewater (San Roque/La Serena)
NPDES Id. No. | NMR10058F |  | Location: |  | 457 Coors Blvd NW
2024-10-29 |  | Owner |  |  |  | Contractor
Operator |  | Thomas Development |  |  |  | HB Construction
Contact name & title |  | Thomas Mannschreck |  |  |  | Jacob Tonks
e-mail |  | tmannschreck@thomasdevelopment.com |  |  |  | jacobt@hbconstruction.com
Contact Phone # |  | 208-343-8877 |  |  |  | 505-549-2189
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2:15pm |  |  |  | Rain
Construction Phase: |  | verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | cloudy |  | Temperature: ~ |  |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-10-19 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The permit coverage posting was missing the NPDES ID# and contact information in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way. It must include the NPDES ID and a contact name and phone number for obtaining additional construction site information per CGP Part 1.5.
2 | Concrete washout had leaked from the washout container in violation of CGP Part 2.3.4. Required mitigation: For washing applicators and containers used for stucco, paint, concrete, form release oils, curing compounds, or other materials: direct wash water into a leak-proof container or leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground per CGP Part 2.3.4. | [9 empty] | Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-09-18
Notes:
SWPPP is at the office for the north portion of construction. Previous SWPPP violations have been mitigated.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action