## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | J10E049 |  | Project Name: |  | Coors/Bluewater (San Roque/La Serena)
NPDES Id. No. | NMR10058F |  | Location: |  | 457 Coors Blvd NW
2025-03-12 |  | Owner |  |  |  | Contractor
Operator |  | Thomas Development |  |  |  | HB Construction
Contact name & title |  | Thomas Mannschreck |  |  |  | Jacob Tonks
e-mail |  | tmannschreck@thomasdevelopment.com |  |  |  | jacobt@hbconstruction.com
Contact Phone # |  | 208-343-8877 |  |  |  | 505-549-2189
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1:15pm |  |  |  | Rain
Construction Phase: |  | verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 60 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | BMPs - The perimeter silt fence needs repair and maintenance in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-01-22
Notes:
SWPPP is in the construction office. Update the inspection reports in the SWPPP.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action