## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [9 empty] | Hope Village; 1215 3rd St. NW
ESC File No. | J14E194 |  | Project Name: |  | Hope Village |  |  |  |  | NMR10033X |  | lalexander@pavilionconstruction.com
NPDES Id. No. | NMR10033X; NMR10033N |  | Location: |  | 1215 3rd St. NW |  |  |  |  | Hope Village, LLC; Michelle DenBleyker
2021-05-25 |  | Owner |  |  |  | Contractor |  |  |  | 432-530-7978
Operator |  | Hope Village, LLC. |  |  |  | Pavilion Construction
Contact name & title |  | Michelle DenBleyker |  |  |  | Lexic Alexander |  |  |  | E2RC | info@e2rc.com
e-mail |  | MDenBleyKer@yeshousing.org |  |  |  | lalexander@pavilionconstruction.com
Contact Phone # |  | 432-530-7978
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: | 12:15 PM/11:45 PM |  |  |  |  | Rain
Construction Phase: |  | Building construction | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  | 78 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [8 empty] | 2021-04-28
1 | Track-out/sediment in the streets/sidewalk. Sweep track-out daily and remove sediment in the streets. | [8 empty] | 2021-05-03
2 | Holes in silt fence. Replace/repair damaged silt fences.
3 | Domestic waste accumulated on East side. Remove domestic waste daily in an approved waste container.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date:
Notes: | Superintendents stated that transients burned holes in the silt fences and contributed to the
accumulation of domestic waste. The track-out pads were removed that day to allow the front-end
loader to transport soil to the truck along the street. The pads will be moved before the site closes
for the day.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action