## Comments
REVIEW COMMENTS
Project: |  | Lobo Plaza TIA |  | PDE:
Review: |  | Draft Dated 9/22/2025 |  | Reviewers:
Date: |  | 2025-12-12 |  | Lee Engineering on behalf of NMDOT
# | PAGE | SECTION | COMMENT | AGENCY | STATUS | RESPONSE
1 | - | Data Collection. | Although traffic data and analysis were to occur at Lomas/Torc Dwy/Frontage Rd, data collection shows 0 volume, indicating no volume or data was not collected. Without existing or future turn volume, the intersection operates at LOS A. | NMDOT
2 | 4 | Study Area Conditions | Page 4. Missing descriptions of signalized intersections. Descriptions should include information on existing configuration, lanes, left turn phasing, signal equipment, vehicle detection systems type, and pedestrian crossings. It is noted that some descriptions are shown on page 7 and could be expanded. | NMDOT
3 | 6 | Analysis of Existing Conditions | Page 6. Pre-TIA documentation states that an analysis of 2025 Existing Conditions would be conducted; however, no analysis was performed. The report indicated this was due to low traffic growth (0.5% /yr), approximating 2028 Background conditions. Existing year analysis should still be conducted per scoping requirements. | NMDOT
4 | 9 | Trip Generation | Page 9. Trip Generation. It is unclear how the 30% pass-by rate was developed since ITE does not provide an AM rate for LUC 932 (42% PM). The 30% does appear to be reasonable. | NMDOT
5 | 17 | Future Volumes | Page 17. Future Volumes. It is unclear to how the trips were applied (pass-by + new) but appear to be a slight over-estimate, therefore okay. | NMDOT
6 | 19 | Capacity Analysis | Page 19, Capacity Analysis, Int. #1 & #2. General Comment. HCS results (poor operation) are significantly different than Synchro results (good operation). Can this difference be explained? | NMDOT
7 | 22 | Capacity Analysis | Page 22, Capacity Analysis, Int #2. Results/timings are significantly different between 2028 No-Build and Build analysis for the NB approach. AM peak hour LOS B should be LOS C for an intersection delay of 21.5 seconds. PM peak hour LOS D should be LOS C for an intersection delay of 32.1 seconds. | NMDOT
8 | 32 | Capacity Analysis | Page 32, The analysis of the site driveways used a 2-stage left-turn movement. With the median opening only 16 feet wide, should the analysis be conducted without staged movements? Drivers may perform more complex routing maneuvers if left turns from driveways operate with high delays. By allowing two stage left turns, is there a safety issue due to limited width and potential back of vehicle extending into opposing through lane? | NMDOT
9 | 33 | Capacity Analysis | Page 33, Capacity Analysis, West Driveway. Analysis indicates all volumes in platoon. NB approach indicates outbound movements at LOS C/D. Can NBL make staged movement with a median width of 16 feet? | NMDOT
10 | 36 | Capacity Analysis | Page 36, Capacity Analysis, East Driveway. Analysis indicates all volumes in platoon. NB approach indicates outbound movements at LOS C/D. Can NBL make staged movement with a median width of 16 feet? | NMDOT
11 | 40 | Queue Analysis | Page 40, Queue Analysis. • Some queue lengths exceed storage length provided. No discussion provided. • Existing conditions and proposed timing optimizations indicate turn length queues exceed turn lane storage lengths. If queues exceed storage and through lanes are blocked by spillback queues, HCS does not provide a means for analysis and a simulation should be performed to assess conditions. • For EBR at Intersection #1 no queues are reported despite yield control; confirm analysis model & parameters. • SBL at intersection #1 has queue storage of ~500FT. Can the turn length designs be mitigated to accommodate the existing/future turn demand? • Add mitigated scenario to “Queuing for NMDOT’ table. | NMDOT
12 | 41 | Recommendations | Page 41, Recommendations. • Intersection #2. No mention of EBL queue extending beyond turn bay, impacts/mitigation. • Intersection #2. No mention of WBR queue extending beyond turn bay, impacts/mitigation. • Intersection #3. No mention of EBL, WBL, and NBL queue extending beyond turn bay, impacts/mitigation. • Intersections #6 and #7. Mitigation should also include fixing any damaged curb, maintaining sidewalks and ramps to be ADA compliant. | NMDOT

## Sheet1
Agree
Disagree
Evaluate
No Action