## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  | Maverik
Location: |  | 1401 Wyoming Blvd NE
Site Contact Name & Agency |  | Jason Bianchetti - Insight |  |  |  | ESC File No. | NMR1001XM
|  | jason@insightnm.con |  |  |  | NPDES Id. No. | J19E049
Inspection Date: |  | 2019-11-21 | Start/End Time: |  | 8:05/8:10AM
CoA Stormwater Inspector: |  |  | Doug Hughes | [9 empty] | Rain
Construction Phase: |  | Vertical | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [8 empty] | 2019-11-19 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Construction Entrance missing, install rock construction entrance
2 | Track out,must be cleaned from adjacent property and prevented in the future.
3 | Maintenance needed on silt fence/mulch sock west side.
Yes
2.1 | Discharge off site? (Y/N) |  |  | Yes | [7 empty] | No
4 | Self Inspection Reports |  |  |  |  | Latest report Date: |  | 2019-08-21
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes 924-3420
|  | jhughes@cabq.gov |  |  |  |  | 2019-11-21

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action