## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  |  | Winrock Town Center Phase B
Location: |  |  | Louisiana and Indian School
Site Contact Name & Agency |  |  | Fred Gorenz - Winrock Properties |  |  |  | ESC File No. | J19E058
|  |  | gorenz@goodmanrealty.com |  |  |  | NPDES Id. No. | NMR100282
Inspection Date: |  |  | 2019-12-11 | Start/End Time: |  | 1000/1025hrs
CoA Stormwater Inspector: |  |  |  | Timothy E. Sims | [9 empty] | Rain
Construction Phase: |  |  | site work and interior renovations | [10 empty] | Clear/ Windy
Type of Inspection: |  | x | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  |  | Clear |  |  | Temperature: ~ |  |  | 39* |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [9 empty] | 2019-11-27 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [13 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | track out on the NW access point to the site requires mitigation. Clean and remove sediment.
2 | Track out on the SE access point to the site requires cleaning and sediment removal.
3 | Waste not in acceptable container. Have trades and subs utilize provided waste containers.
4 | Inlet protection is require for the inlet east of NM Orthopedics entrance. Coco mat or mulch sock
addresses this issue.
5 | Please provide latest SWPPP self-inspection report.
Yes
2.1 | Discharge off site? (Y/N) |  |  |  | No | [7 empty] | No
4 | Self Inspection Reports |  |  |  | requested |  | Latest report Date: |  | 2019-10-14
Notes: | Material is being hauled out of both access points, Lalo w/TLC, started cleaning between
deliveries with mechanical broom.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  |  | Timothy E. Sims - (505) 803-6155
|  |  | tsims@cabq.gov |  |  |  |  | 2019-12-11

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action