## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  | Winrock Towne Center Phase B
Location: |  | Louisiana and Indian School
Site Contact Name & Agency |  | Fred Gorenz |  |  |  | ESC File No. | J19E058
|  | Winrock Partners, LLC |  |  |  | NPDES Id. No. | has not appeared to have filed an NOI
Inspection Date: |  | 2019-07-02 | Start/End Time: |  | 8:50/9:45
CoA Stormwater Inspector: |  |  | Curtis Cherne | [9 empty] | Rain
Construction Phase: |  | demo 2 areas, installing utilities | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint | X | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2019-05-10 | [5 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Owner has not submitted an NOI or an Erosion and Sediment Control plan
2 | Sediment and black sludge outside work area and no inlet protection - NE area
3 | sediment outside work area along southern edge of NE Area
4 | No vehicle tracking control NE area
5 | No inlet protection anywhere
6 | no Vehicle Tracking Control NE area
7 | Sediment and wastes entering drainage system
8 | Domestic and construction waste not in an acceptable waste container-demo south
9 | No sediment BMP south edge NE area
Yes
2.1 | Discharge off site? (Y/N) |  |  | Yes | [7 empty] | No
4 | Self Inspection Reports |  |  |  |  | Latest report Date: |  | no reports
Notes:
west area where TLC is working was in compliance
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Curtis Cherne PE, 505-924-3420
|  | ccherne@cabq.gov |  |  |  |  | 2019-07-02

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action