## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | J219E088 |  | Project Name: |  | Presbyterian Kaseman Hospital Southeast Parking Lot
NPDES Id. No. | NMR1005EO & NMR1005EH |  | Location: |  | 8324 Constitution Pl. NE
2024-03-07 |  | Owner - |  |  |  | Contractor
Operator |  | Presbyterian Healthcare Services |  |  |  | Platinum Builders Corp.
Contact name & title |  | Diana Lamb |  |  |  | Wayne Mitchell
e-mail |  | dlamb3@phs.org |  |  |  | wayne@pbcnm.com
Contact Phone # |  | 505-563-6632 |  |  |  | 505-352-8897
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 1:15PM |  |  |  | Rain
Construction Phase: |  | C&G complete subgrade ready for paving | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-02-10 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | BMPs - the silt fence had holes in it, but most of the site was too low to drain to off-site streets. Required Mitigation: Ensure that all stormwater controls (BMPs) are maintained and remain in effective operating condition during permit coverage per CGP 2.1.4. If at any time you find that a stormwater control needs routine Maintenance, you must immediately initiate the needed maintenance work and complete such work by the close of the next business day. When the problem requires a new or replacement control or significant repair, install the new or modified control and make it operational, or complete the repair, by no later than seven (7) calendar days from the time of discovery per CGP 5.2.1.
2 | The SWPPP wasn't available on site, the superintendent was absent, and there was no answer when I called the number on the sign in violation of CGP 7.3. Required Mitigation: The SWPPP, including the SWPPP Map, Self Inspection Reports, and Corrective Action Reports, must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site CGP 7.3.
3
2.1 | Discharge off site? (Y/N) | [9 empty] | Yes
4 | Self Inspection Reports |  |  | missing | Latest report Date: |  | missing |  |  |  | Yes
Notes:
The sign said to call Jason Ford at 337-9957 for the SWPPP.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action