## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | J20E028 |  | Project Name: |  | NuVue
NPDES Id. No. | NMR10069N/NMR10069Z |  | Location: |  | 1171 Jaffa Rd. NE
2025-03-10 |  | Owner - |  |  |  | Contractor
Operator |  | 4740 Dillon Drive, LLC |  |  |  | Harrison Construction LLC
Contact name & title |  | Malik Hasan |  |  |  | Patrick Audenis
e-mail |  | accounts@nuvuepharma.com |  |  |  | harrisonbuildinginc@hotmail.com
Contact Phone # |  | 919-619-2443 |  |  |  | 949-278-1727
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | graded, stockpiles | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 60 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-11-07 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Stabilization - This site has been inactive for multiple months with no stabilization measures installed in violation of CGP Part 2..2.14. Required mitigation: Initiate the installation of stabilization measures immediately in any areas of exposed soil where construction activities have permanently ceased or will be temporarily inactive for 14 or more calendar days per CGP Part 2.2.14.
2 | BMPs - The perimeter silt fence needs replacing in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | no
4 | Self Inspection Reports |  |  | ok | Latest report Date: |  | 2024-05-28 |  |  |  | no
Notes:
The SWPPP is in a bucket east of the entrance. The posting sign is starting to fade. There are multiple holes and gaps in the perimeter construction fence.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action