## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | J20E028 |  | Project Name: |  | NuVue
NPDES Id. No. | NMR10069N & NMR10069Z |  | Location: |  | 1171 Jaffa Rd. NE
2025-04-14 |  | Owner - |  |  |  | Contractor
Operator |  | 4740 Dillon Drive, LLC |  |  |  | Harrison Construction LLC
Contact name & title |  | Malik Hasan |  |  |  | Patrick Audenis
e-mail |  | accounts@nuvuepharma.com |  |  |  | harrisonbuildinginc@hotmail.com
Contact Phone # |  | 919-619-2443 |  |  |  | 949-278-1727
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | footer excavation | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 60 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-11-07 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Posting - The permit coverage posting sign was missing in violation of CGP Part 1.5. Required mitigation: You must post a sign or other public notice of your permit coverage at a safe, publicly available location in close proximity to the construction site per CGP Part 1.5. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way.
2 | BMPs - The silt fence has not been maintained and has collapsed in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
3
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | no
4 | Self Inspection Reports |  |  | ok | Latest report Date: |  | 2025-03-29 |  |  |  | no
Notes:
The replacement SWPPP was in a bucket east of the entrance, was inspected on 4/4/25, and only had two self-inspection reports. The SWPPP certifications weren't signed, and the delegation of authority to Paul Julian was missing.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action