## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | J20E028 |  | Project Name: |  | NuVue
NPDES Id. No. | NMR10069N & NMR10069Z |  | Location: |  | 1171 Jaffa Rd. NE
2025-04-07 |  | Owner - |  |  |  | Contractor
Operator |  | 4740 Dillon Drive, LLC |  |  |  | Harrison Construction LLC
Contact name & title |  | Malik Hasan |  |  |  | Patrick Audenis
e-mail |  | accounts@nuvuepharma.com |  |  |  | harrisonbuildinginc@hotmail.com
Contact Phone # |  | 919-619-2443 |  |  |  | 949-278-1727
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | graded, stockpiles | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-08-10 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | BMPs - There are multiple holes in the perimeter silt fence which is also not entrenched in violation of CGP Part 2.1.4. All of the silt fence needs reset.Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
2 | Posting - The permit coverage posting had faded and was not legible in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way per CGP Part 1.5.
3 | Stabilization - This site has been inactive for multiple months with no stabilization measures installed in violation of CGP Part 2..2.14. Required mitigation: Initiate the installation of stabilization measures immediately in any areas of exposed soil where construction activities have permanently ceased or will be temporarily inactive for 14 or more calendar days per CGP Part 2.2.14.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | no
4 | Self Inspection Reports |  |  | ok | Latest report Date: |  | 2024-03-29 |  |  |  | no
Notes:
The SWPPP is in a bucket east of the entrance. SWPPP was not inspected due to homeless activity at the gate during the inspection. The inspection was a perimeter check.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action