## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | J22E050 |  | Project Name: |  | Albuquerque School of Excellence
NPDES Id. No. | NMR1002OT |  | Location: |  | 13201 Lomas Blvd NE
2020-09-15 |  | Property Owner |  |  |  | Contractor
Operator |  | Albuquerque School of Excellence |  |  |  | EPPX
Contact name & title |  | Eugene Eski |  |  |  | Juan Olivas
|  | teski@harmonyed.org |  |  |  | jolivas@eppx.net
Contact Phone # |  | 713-900-7173 |  |  |  | 505-225-4781
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 2:30-3:30PM |  |  |  | Rain
Construction Phase: |  | Parking lot paqving and lands | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 76 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [11 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | BMPs (silt fence) missing.
2 | Sediment on the sidewalk. Remove same day.
3 | Roof drains are causing erosion and need to drain to pond.
4 | SWPPP is not up-to-date, map needs updated per GP 7/20/20 (attached) and signatures needed.
Yes
2.1 | Discharge off site? (Y/N) |  |  | yes | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | 2020-09-14
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action