## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [11 empty] | NMR1002OT |  | School of Excellence
ESC File No. | J22E050 |  | Project Name: |  | Albuquerque School of Excellence | [8 empty] | 13201 Lomas
NPDES Id. No. | NMR1002OT |  | Location: |  | 13201 Lomas Blvd. NE | [8 empty] | Eugene Eski harmony edu
2023-04-05 |  | Owner |  |  |  | Contractor | [7 empty] | 713-900-7173
Operator |  | Albuquerque School of Excellence |  |  |  | EPPX
Contact name & title |  | Eugene Eski |  |  |  | Juan Olivas
e-mail |  | teski@harmonyed.org |  |  |  | jolivas@eppx.net | [7 empty] | EPPX
Contact Phone # |  | 713-900-7173 |  |  |  | 505-225-4781 | [7 empty] | Juan Olivas
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 12:25 PM/12:30 PM |  |  |  |  | Rain | 505-225-4781
Construction Phase: |  | Plan revision phase 2 | [10 empty] | Clear/ Windy | jolivas@eppx.net
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 78 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2023-03-16 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | None. | [9 empty] | 2021-05-03
2 | The Final Stabilization Criteria CGP2.2.14.c has been satisfied. Now you must remove the BMPs and send documentation of the Final Stabilization to the EPA with a Notice of Termination (NOT) per CGP 8.2 to end your coverage under the CGP. This step is independent of the Certificate of Occupancy. Please copy me with the documentation and the EPA’s acceptance of the NOT.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2021-04-12
Notes: | Coverage under 2017 permit expired
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action