## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K08E003 |  | Project Name: |  | West Mesa RV Park
NPDES Id. No. | NMR1003H4 |  | Location: |  | Volcano Rd. and 102nd Street
2021-01-27 |  | Owner |  |  |  | Contractor
Operator |  | SM Quraishi |  |  |  | Shakeel Rizvi
Contact name & title |  | SM Quraishi |  |  |  | Shakeel Rizvi
e-mail |  | smquraishi@yahoo.com |  |  |  | shaky1424@yahoo.com
Contact Phone # |  | 379-6643 |  |  |  | 315-6563
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 3pm |  |  |  | Rain
Construction Phase: |  | infrastructure complete | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2020-12-11 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | This site has disrupted the drainage pattern into the Citys pond south of this site and will be responsible for repares to the City's pond.
2 | BMPS must be added to the SWPPP Map and in the field around the Work Order area of disturbance.
3 | Silt fence was incomplete on the north side of the site.
4 | Ponds are to be the first item of earthwork construction and should help mitigate potential damage to the City's pond.
5 | Stabelization is required for all areas inactive for 14 days.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | 2021-02-04
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action