## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K08E003 |  | Project Name: |  | Paradise RV Park Phase 2
NPDES Id. No. | NMR1006HM |  | Location: |  | Volcano Rd. and 102nd Street
2025-10-29 |  | Owner |  |  |  | Contractor
Operator |  | West Mesa RV Park, LLC
Contact name & title |  | Karan Rai
e-mail |  | karanveer.rai@gmail.com
Contact Phone # |  | 760-783-6599
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 10am |  |  |  | Rain
Construction Phase: |  | C&G in the south half of Phase 2, but WO has not started. | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-10-14 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | NOI - Phase 2 construction began a year ago without submitting the property owner's Notice of Intent and ESC Plan to the City for approval. The NOIs and ESC Plans submitted on 8/27/25and 10/7/25 contained deficiencies that were sent to you on 9/3/25 and 10/17/25, which must be addressed before approval. Required Mitigation: The property owner’s NOI is acceptable, but the off-site construction support activities and upstream BMPs are still not shown on the ESC Plan. The ESC Plan must be submitted to the City of Albuquerque for review and approval in accordance with Albuquerque’s Erosion and Sediment Control (ESC) ordinance § 14-5-2-11(A). Include county acceptance of past and planned land disturbance west of 102nd. St.
2 | BMPs - There are still not any BMPs to prevent upstream offsite stormwater from being diverted by the phase 2 construction into Volcano Rd and the city's pond south of this site. The Phase 1 on-site pond was filled a year ago during the unauthorized start of Phase 2 earthwork. The Phase 2 block wall along 102nd St., built over two years ago, further contributed to erosion on Volcano Rd and City Pond NE2 south of the site, violating city Ordinance § 14-5-2-12(B)(3). It didn't rain since the last inspection, so there wasn't any new erosion or sediment. Required mitigation includes diverting upstream off-site stormwater around disturbed areas with temporary compacted berms, swales, or storage in temporary sediment basins. The CGP requires a design for 2-year storms according to CGP 2.2.12, and City Ordinance § 14-5-2-12(B)(3) mandates a 10-year storm design from May 1 through October 31. The design must include retention of the upstream offsite stormwater and prevent flows from reaching the area of erosion on Volcano Rd. and the City's pond. Provide design calculations and construction specifications on the ESC Plan stamped by a registered PE to the city for approval, and construct the BMPs immediately.
2.1 | Discharge off site? (Y/N) |  |  | yes | [6 empty] | No
4 | Self Inspection Reports |  |  | ? | Latest report Date: |  | ?
Notes: | SWPPP is in main office.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action