## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K08E004 |  | Project Name: |  | Mister Carwash
NPDES Id. No. | NMR1002LG |  | Location: |  | 201 98th St.
2021-07-01 |  | Owner |  |  |  | Contractor
Operator |  | Dave Hail |  |  |  | HBA CORP Construction
Contact name & title |  | Dave Hail |  |  |  | Martin Armijo
e-mail |  | Dhail@mistercarwash.com |  |  |  | marmijo@benningconstruction.com
Contact Phone # |  | 520-907-8130 |  |  |  | 505-916-6463
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 11:15 AM-11:20 AM |  |  |  | Rain
Construction Phase: |  | Stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 79 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-06-28 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | No posting of permit coverage. Re-post permit coverage in a location visible to the public. | [9 empty] | 2021-05-03
2 | Install perimeter control BMP. A sediment control BMP needs to be installed and maintained until final stabilization is accepted by the City.
3 | Provide self-inspection reports. Inspection reports must continue every 14 days until final stabilization is accepted by the City.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-08-13
Notes: | Spoke with Martin and discussed the final stabilization criteria and actions to be taken.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action