## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E002 |  | Project Name: |  | 9101 Central Ave NW
NPDES Id. No. | NMR1006B5 |  | Location: |  | 9101 Central Ave NW
2025-05-05 |  | Owner |  |  |  | Contractor
Operator |  | Cosme Jaquez |  |  |  | Cosme Jaquez
Contact name & title |  | Cosme Jaquez |  |  |  | Cosme Jaquez
e-mail |  | jaquez.aylin14@gmail.com |  |  |  | jaquez.aylin14@gmail.com
Contact Phone # |  | 505-250-7216 |  |  |  | 505-250-7216
COA Inspector |  | James Hughes |  |  |  | start |  | 11:30am |  |  |  | Rain
Construction Phase: |  | earthwork | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? | [5 empty] | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-05-04 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Posting - CGP coverage was not posted too far from the Street. It isn't visible from the public road in violation of CGP 1.5. Required Mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way per CGP 1.5.
2 | The SWPPP and self-inspection reports were not available on-site during the inspection in Violation of CGP 7.3, City Ordinance § 14-5-2-11(C)(1), and CGP 4.7.3. No construction personnel were present at the time of inspection, and the sign indicating the location of the SWPPP was missing in violation of CGP 7.3. Required Mitigation: The SWPPP, including the SWPPP Map, Self-Inspection Reports, and Corrective Action Reports, must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site CGP 7.3.
3 | BMPs - The Silt Fence was attached to a mobile chain-link fence, so it wasn't properly installed, in violation of CGP 2.1 and CGP 2.2.3. Required mitigation: The silt fence must be reset, attached to stationary stakes with the fabric embedded 12"into the ground, in accordance with the Corrective Action requirements of CGP 5.2.1, no later than seven (7) calendar days from the time of discovery. If at any time you find that a stormwater control needs routine Maintenance, you must immediately initiate the necessary maintenance work and complete it by the close of the next business day.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | requested | Latest report Date: |  | ?
Notes:
The SWPPP was not available on site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action