## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E026D & K09E047 (WO) |  | Project Name: |  | Westpointe Data Center & Titan's Stockpile @ Daytona
NPDES Id. No. | NMR1006JH & NMR1004LY |  | Location: |  | 8401 Daytona Rd. NW
2024-08-28 |  | Owner |  |  |  | Contractor
Operator |  | 98th and I-40 Land, LLC |  |  |  | Titan Development
Contact name & title |  | Brian Patterson |  |  |  | Brian Patterson
e-mail |  | bpatterson@titan-development.com |  |  |  | bpatterson@titan-development.com
Contact Phone # |  | 505-998-0163 |  |  |  | 505-998-0163
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 10:30 |  |  |  | Rain
Construction Phase: |  | Stockpile | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 69 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-08-27 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Sediment had been discharged in stormwater or tracked out from the site and deposited in the adjacent street and not removed within 24 hours in violation of CGP 2.2.4.d. Required mitigation: Remove sediment deposited in the streets by the end of the same business day. Remove the sediment by sweeping, shoveling, or vacuuming these surfaces or using other similarly effective means of sediment removal. You are prohibited from hosing or sweeping sediment per CGP 2.2.4.d.
2 | BMPs - Erosion and sediment controls were not implemented and maintained to minimize the discharge of pollutants in stormwater from this site in violation of CGP 2.1. Specifically, sediment basins and silt fences are missing from the Westpointe data Center. There were no perimeter controls on the lots to keep sediment and other pollutants out of the street in violation of CGP 2.2.3. Required mitigation: If at any time you find that a stormwater control needs routine Maintenance, you must immediately initiate the needed maintenance work and complete such work by the close of the next business day. When the problem requires a new or replacement control or significant repair, install the new or modified control and make it operational or complete the repair by no later than seven (7) calendar days from the time of discovery per CGP 5.2.1.
Yes
2.1 | Discharge off site? (Y/N) |  |  | Yes | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-08-06
Notes: | SWPPP in box attached to the back of the posting.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action