## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E026D |  | Project Name: |  | Westpointe Data Center
NPDES Id. No. | NMR1006JH & NMR1006VQ |  | Location: |  | 8401 Daytona Rd. NW
2025-05-05 |  | Owner |  |  |  | Contractor
Operator |  | CLOP Albuquerque NM LLC |  |  |  | PARIC Corporation
Contact name & title |  | David Scott |  |  |  | Kevin Ruck
e-mail |  | dave@oppidan.com |  |  |  | KMRuck@paric.com
Contact Phone # |  | 952-294-0353 |  |  |  | 636-698-8299
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 10:30 |  |  |  | Rain
Construction Phase: |  | Slab and one tilt wall | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | cloudy |  | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-05-04 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | BMPs - Erosion and sediment controls were not implemented and maintained as shown on the approved ESC Plan dated 10/17/24 in violation of CGP 2.1. Specifically, sediment basins and swales are missing all accross the south side of this site. Required mitigation: If at any time you find that a stormwater control needs routine Maintenance, you must immediately initiate the needed maintenance work and complete such work by the close of the next business day. The mising ponds and swales are part of a "Corrective Action" so they must be installed and made operational by no later than seven (7) calendar days from the time of discovery per CGP 5.2.1. You must also complete a Corrective Action Report.
2 | The SWPPP and self-inspection reports were missing the owner/operator's signature on the certification statements. Two people from PARIC Corporation signed each report, and no one from CLOP Albuquerque, NM LLC., in violation of CGP G.11.2. The approved SWPPP Map dated 10/17/2024 was missing from the SWPPP. Required Mitigation: Since you have not delegated your signature authority to an employee, you personally must sign the certification statements on the SWPPP and all reports. You may not delegate your signature authority to an employee of a third party outside of the CLOP Albuquerque NM LLC. The SWPPP, including the SWPPP Map, Self-Inspection Reports, and Corrective Action Reports, must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site CGP 7.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-04-28
Notes: | The SWPPP is in the construction trailer.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action