## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E041 |  | Project Name: |  | Westpoint 40
NPDES Id. No. | NMR1002M |  | Location: |  | 98th Street and Bluewater | [6 empty] | Brian Patterson <bpatterson@Titan-Development.com>
2021-07-08 |  | Owner |  |  |  | Contractor
Operator |  | Titan Development
Contact name & title |  | Brian Patterson
e-mail |  | bpatterson@Titan-Development.com
Contact Phone #
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 9:35 AM-9:45 AM |  |  |  |  | Rain
Construction Phase: |  | Temporary stabilization | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 74 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2021-07-06 |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Self-inspection reports not received upon last request.
2 | Section of silt fence along Bluewater Rd. needs repair. Repair/replace silt fence.
3 | Maintain temporary stabilization controls. Identify type of mulch used, dates of application, and rates of application.
4 | Remove and dispose of domestic waste
5
6
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-08-02
Notes: | No activity on the site. Spoke with Brian via phone on 7/9/21. The mulch was applied
approximately 10 months ago and is holding well. However, some areas may need to be mulched
again.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action