## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E043 |  | Project Name: |  | L&C Transport Office & Shop | [5 empty] | lorenaj89@gmail.com
NPDES Id. No. | NMR10032W |  | Location: |  | 112 94th Street NW | [5 empty] | tim Slatunas
2021-05-13 |  | Owner |  |  |  | Contractor
Operator |  | F&J Homebuilders | [8 empty] | Matt Vallejos | matt@greenglobenm.com
Contact name & title |  | Freddie Lopez |  |  |  | Lorena
e-mail |  | fjhomebuilders@yahoo.com |  |  |  | lorenaj89@gmail.com |  |  |  |  | mario@greenglobenm.com
Contact Phone # |  | 505-362-1790
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 3:00 PM/3:05 PM |  |  |  |  | Rain
Construction Phase: |  | Building Construction/earthwork | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 80 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | No BMPs on North and West fence lines. Install sediment control BMPs to prevent sediment from exiting the site. | [9 empty] | 2021-05-03
2 | Washout on the ground. Direct wash water from concrete, paint, and stucco into a leak-proof container per CGP 2.3.4. Removed and dispose hardened washout with other waste per CGP 2.3.3
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-06-18
Notes: | No activity on site during this inspection.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action