## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E044 |  | Project Name: |  | Maverik - 98th and Bluewater
NPDES Id. No. | NMR1002R2 |  | Location: |  | 9701 Bluewater Rd. NW | [5 empty] | Kelly Irons <Kelly.Irons@maverik.com>
2021-04-26 |  | Owner |  |  |  | Contractor
Operator |  | Maverik
Contact name & title |  | Kelly Irons
e-mail |  | Kelly.Irons@maverik.com
Contact Phone # |  | 801-335-3815
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 1:25 PM/1:50 PM |  |  |  | Rain
Construction Phase: |  | Stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-02-22 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Areas along West and South frontages are not stabilized. Implement final stabilization controls.
2
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-08-03
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action