## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E047 (WO) |  | Project Name: |  | Stockpile at 98th and I-40 @ Daytona
NPDES Id. No. | NMR1004LY |  | Location: |  | Bluewater Rd and 98th St NW
2023-06-05 |  | Owner |  |  |  | Contractor
Operator |  | Titan Development
Contact name & title |  | Brian Patterson
e-mail |  | bpatterson@titan-development.com
Contact Phone # |  | 505-998-0163
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: | 2pm |  |  |  | Rain
Construction Phase: |  | Stockpiling | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2023-05-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Self inspections and routine maintenance for BMPs must continue until disturbed land is stabilized. Ensure that all stormwater controls (BMPs) are maintained and remain in effective operating condition during permit coverage per CGP 2.1.4. If at any time you find that a stormwater control needs routine Maintenance, you must immediately initiate the needed maintenance work and complete such work by the close of the next business day. When the problem requires a new or replacement control or significant repair, install the new or modified control and make it operational, or complete the repair, by no later than seven (7) calendar days from the time of discovery per CGP 5.2.1.
2 | It appears that the site has been inactive for over 14 days. Implement and maintain stabilization measures in areas that remain inactive for 14 days or more. Measures must be initiated within 14 days and complete the installation not later than 14 days. Stabilize the inactive disturbed areas. Keep record of the stabilization methods, materials, rates and dates of each application with the SWPPP and provide copies.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date:
Notes: | An electronic version of the SWPPP was sent by the operator
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action