## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E047 |  | Project Name: |  | Southern Tire Mart
NPDES Id. No. | NMR10044B/NMRNMR10043H |  | Location: |  | 8201 Daytona Rd NW
2021-12-14 |  | Owner NMR10044B |  |  |  | Titan NMR10045T
Operator |  | Southern Tire Mart, LLC |  |  |  | Sparling NMR10043H
Contact name & title |  | Rick Yarbrough |  |  |  | Pat Wylle
e-mail |  | rick.yarborough@stmtires.com |  |  |  | pwylie@sparlingconstruction.net
Contact Phone # |  | 505-917-6442 |  |  |  | 821-1034
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 8:00 |  |  |  | Rain
Construction Phase: |  | Vertical | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 78 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-09-30 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | None | [9 empty] | 2021-05-03
2 | [10 empty] | 2021-05-31
3
1. Remove tumbleweeds (City Ordinance § 9-8-4)
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | n/a | Latest report Date: |  | 2021-12-13
Notes: | WorkOrder ready for paving. Site was raised and is now inactive.
SWPPP certification signed by Titan and Sparling, not Southern Tire Mart. Not any valid Deligation of Authority. Southern Tire mart will have different SWPPP after site is transferred.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-803-6155)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action