## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E048 |  | Project Name: |  | Avalon Subdivision
NPDES Id. No. | NMR10050Y |  | Location: |  | 98th St NW and Bluewater Rd NW
2023-07-21 |  | Owner |  |  |  | Contractor
Operator |  | RS Bluewater LLC
Contact name & title |  | Ashley Klein
e-mail |  | ashley@redskyholdings.com
Contact Phone # |  | 504-428-4111
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: | 10AM |  |  |  | Rain
Construction Phase: |  | N/A, unstabilized | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  | 94 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2023-05-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The posted Permit coverage isn't ledgable from the street, the font is too small It violates CGP 1.5. Required Mitigation: You must post a sign with a font large enough to be readily viewed from a the street. At a minimum , the notice must include: a) NMDES ID, b) name and phone number for additional infomation, and c) the URL for the SWPPP (if available), and d) note how to contact EPA in case of polution.
2 | Your SWPPP and Self inspection reports were not available on-site during the inspection in violation of City Ordinance § 14-5-2-11(C)(1) and in violation of CGP 7.3. Notice of the SWPPP location wasn't posted also in violation CGP 7.3. Required Mitigation: The SWPPP must be kept up-to-date per CGP 7.1 and available on-site per CGP 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site per CGP 7.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date:
Notes: | No SWPPP available at time of inspection. Coverage is active
As a reminder, in accordance with City Ordinance § 14-5-2-11(C)(1), self-inspections must continue until the site is “determined as stabilized by the city.” The property owner/operator is responsible for determining when the “Conditions for Terminating CGP Coverage” per CGP Part 8.2 are satisfied and then for filing their Notice of Termination (NOT) with the EPA. Each operator may terminate CGP coverage only if one or more of the conditions in Part 8.2.1, 8.2.2, or 8.2.3 has occurred. After filing the NOT with the EPA, the property owner is responsible for requesting a Determination of Stabilization from the City.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action