## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E048 |  | Project Name: |  | Avalon Subdivision
NPDES Id. No. | NMR10050Y |  | Location: |  | 98th St NW and Bluewater Rd NW
2024-08-28 |  | Owner |  |  |  | Contractor
Operator |  | RS Bluewater LLC |  |  |  | RS Bluewater LLC
Contact name & title |  | Kenin Mattson |  |  |  | Phil Choquette
e-mail |  | kmattson@redskyholdings.com |  |  |  | phil@redskyholdings.com
Contact Phone # |  | 972-369-4123 |  |  |  | 918.760.7793
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 1:45PM |  |  |  | Rain
Construction Phase: |  | Stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 69 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-08-27 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP wasn't available on-site at the time of inspection, nor was it provided in a timely manner when requested in violation of CGP 7.3. Final Stabilization was missing from the permanent pond(s) in the southerly 0.5 acres of Tract F. and on the north part of tract B next to Sonic. Required Mitigation: The SWPPP, including the SWPPP Map, Self-Inspection Reports, and Corrective Action Reports, must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3, and 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, a notice of the plan’s location must be posted near the main entrance of your construction site CGP 7.3. The SWPPP must contain at least four SWPPP Modifications per CGP 7.4.1.b and 7.4.2, one modification for each of the four transfers, and the division of Tract F into F1 and F2. Include authorizations per CGP 7.4.3. Update the NOI Point of Contact. Show the division of Tract F into F1 and F2 and specify weed maintenance and Final Stabilization of the ponds on the south 0.5 acres of Tract F2. Clarify which ponds are permanent and which ponds are temporary, and which ponds go with which lots. Provide pond stabilization per STD DWG 1013 for all permanent ponds.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | ? | Latest report Date: |  | ?
Notes: | New point of contact, Phil, isn't in SWPPP or NOI.
The Division of tract F hasn't been planned and landscaping ponds on south end of tract F is controversial. SWPPP was stolen from site the same week that Calaber Collision applied.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes 924-3420
jhughes@CABQ.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action