## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E048B |  | Project Name: |  | Dutch Brothers
NPDES Id. No. | NMR1005FQ |  | Location: |  | 210 98th St NE
2023-08-30 |  | Owner |  |  |  | Contractor
Operator |  | Heritage Trails Development, LLC
Contact name & title |  | John Caglia
e-mail |  | john.caglia@dutchbros.com
Contact Phone # |  | 714-883-9092
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1030am |  |  |  | Rain
Construction Phase: |  | infrastructure nearly complete | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 85 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-08-08 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The permit coverage posting was missing in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5.
2 | The SWPPP and inspection reports were unavailable for the inspection in violation of CGP Parts 4.7.3 and 7.3. Construction equipment stored and land disturbance off-site that is not marked on the ESC Plan map submitted to the city in violation of CGP Part 7.2.4. Required mitigation: You must keep a current copy of your SWPPP and all inspection reports at the site or at an easily accessible location so that it can be made available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3. The site map must include locations of on-site and off-site construction support activities per CGP Part 7.2.4.b.vii.
3 | The are multiple gaps in the perimeter silt fence in violation of CGP Parts 2.1.2 and 2.1.4. Required mitigation: You must design and install all stormwater controls in accordance with good engineering practices, including applicable design specifications per CGP Part 2.1.2. You must ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action