## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | K09E048B |  | Project Name: |  | Dutch Brothers
NPDES Id. No. | NMR1005FQ |  | Location: |  | 210 98th St NW
2023-09-14 |  | Owner |  |  |  | Contractor
Operator |  | Heritage Trails Development, LLC
Contact name & title |  | John Caglia |  |  |  | Joseph Green
e-mail |  | john.caglia@dutchbros.com |  |  |  | jgcsdevelopment@gmail.com
Contact Phone # |  | 714-883-9092 |  |  |  | 469-888-3285
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1030am |  |  |  | Rain
Construction Phase: |  | infrastructure nearly complete | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-09-13 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The permit coverage posting was missing in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5.
2 | The SWPPP was available for this inspection, but it is missing multiple items, including self-inspection reports in violation of CGP 7.2 and City Ordinance 14-5-2-11. The Stormwater Team is unidentified by name and position in violation of CGP Part 7.2.2 and the self-inspection reports were unavailable in violation of CGP Part 4.7.3. Required mitigation: Identify individuals responsible for a) design of BMPs, b) installation of BMPs, c) maintenance of BMPs, d) repair of BMPs, e) treatment chemicals (if applicable), f) conducting inspections, and g) taking corrective actions according to CGP Parts 6 and 7.2.2. Perform self-inspections according to CGP Part 4 and make available for inspections per CGP Part 4.7.3 and City Ordinance 14-5-2-11.
3 | The are multiple gaps in the perimeter silt fence in violation of CGP Parts 2.1.2 and 2.1.4. Subcontractors are not using the designated construction exit and instead using a low point of the site for access in violation of CGP Part 2.2.4. Required mitigation: CGP Part 2.1.2 requires you to design and install all stormwater controls in accordance with good engineering practices, including all design specifications. You must install sediment controls along any perimeter areas of the site that are downslope from any exposed soil or other disturbed areas per CGP Part 2.2.3. To minimize track-out, you must restrict vehicle use to properly designated exit points and use appropriate stabilization techniques at all points that exit onto paved roads, according to CGP Part 2.2.4.
4 | There were spots of concrete washout on the ground and the site is missing a designated washout container in violation of CGP Part 2.3.4. Required mitigation: CGP Part 2.3.4 requires you to direct wash water into a leak-proof container or leak-proof and lined pit and to not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
Previos violations were missing Posting, missing SWPPP, and BMPs. The only operator identified is Dutch Bros, LLC since there is no contractor NOI.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action